## Stakeholder Map
Stakeholder group | Influence (1-5) | Interest (1-5) | Current attitude (-2 to +2) | Desired attitude by Week 8 | Key concerns (hypothesis) | Expected benefits | Engagement priority | Evidence to validate
Board / Executive | 5 | 4 | 1 | +2 Champion | Return on investment; reputational risk; delivery timeline; forecast reliability | Better visibility, improved service, working-capital control | Manage closely | Interview notes; steering-group questions
Plant heads | 5 | 5 | 0 | +1 Supportive | Production disruption; unrealistic plans; accountability for missed targets | More stable schedules; earlier visibility of demand changes | Manage closely | Plant interviews; schedule-change examples
Planners | 4 | 5 | -2 | 0 Neutral or better | Loss of control; model replacing judgement; blame for model errors; extra workload | Less manual consolidation; earlier exception signals; more time for judgement | Highest adoption priority | Planner forum; pulse survey; workflow observation
Sales | 4 | 4 | 0 | +1 Supportive | Forecast misses promotions, customer changes, or one-off orders | Improved alignment with production; clearer availability discussions | Keep engaged | Sales interviews; promotion/order-change examples
Procurement | 4 | 4 | 0 | +1 Supportive | Unstable recommendations; supplier lead times; excess or shortage risk | Earlier material visibility; more structured buying decisions | Manage closely | Buyer interviews; shortage/overstock examples
IT / Data team | 4 | 3 | 1 | +1 Supportive | Data quality; integrations; access control; support burden | Clearer data ownership; monitored model performance; fewer ad hoc requests | Keep satisfied and involved | Technical review; data-quality log
Finance | 4 | 3 | 0 | +1 Supportive | Benefits not measurable; inventory costs; uncertain assumptions | Quantified working-capital and service outcomes | Keep informed and validate benefits | Finance review; agreed KPI definitions
Key yarn supplier | 3 | 3 | 0 | 0 to +1 Cooperative | Forecast mistaken for firm order; lead-time volatility; capacity and MOQ constraints | Better forward visibility and fewer last-minute surprises | Coordinate actively | Supplier review; lead-time and MOQ confirmation

## Engagement Strategy
Stakeholder group | Core message | Channel / format | Frequency | Message owner | Feedback mechanism | Adaptation
Board / Executive | Pilot is controlled; value, risk, and decisions are visible. | Executive dashboard and steering review | Monthly; urgent risks as needed | Project sponsor / project lead | Decision log; sponsor Q&A | Concise, outcome-led, highlight decisions and trade-offs
Plant heads | Forecast supports planning; operational constraints remain part of decisions. | Operations review and site huddles | Fortnightly; weekly during pilot start | Operations lead | Exception log; plant review | Practical impacts, schedule examples, clear action owners
Planners | Planner expertise remains essential; challenge and improve recommendations. | Hands-on demos, planner forum, office hours | Weekly during pilot; fortnightly pulse survey | Planning lead / change lead | Pulse survey; forecast challenge log | Detailed examples, show override/exception workflow, acknowledge concerns
Sales | Customer knowledge and promotion context must inform forecasts. | Sales meeting and short written update | Fortnightly; before major promotions | Sales lead | Demand-change form; sales feedback log | Customer and promotion examples; avoid technical jargon
Procurement | Use forecasts as planning signals; validate lead time, stock, and approvals. | Procurement review and dashboard | Weekly during pilot | Procurement lead | Material-risk log; supplier feedback | Show item, timing, confidence/exception, and approval requirement
IT / Data team | Reliable data, monitoring, access, and support underpin trust. | Technical stand-up and issue tracker | Weekly | IT lead / data owner | Defect tracker; data-quality dashboard | Technical detail, root causes, owners, and service levels
Finance | Benefits will be assessed with agreed measures and baseline. | Monthly benefit review and dashboard | Monthly | Finance business partner | KPI review; assumptions log | Show baseline, calculation, uncertainty, and cost/benefit trade-offs
Key yarn supplier | Forecast is indicative until confirmed through normal ordering. | Supplier call and written forecast summary | Monthly; weekly for material exceptions | Procurement lead | Lead-time/MOQ feedback; supplier action log | Clear estimate-versus-order labels, changes, and notice period

## 12-Week Calendar
Week | Purpose | Key activity / communication | Audience | Channel | Owner | Feedback / evidence | Success measure
1 | Align leadership | Kick-off: objectives, scope, risks, governance, decisions needed | Board, plant heads, functional leads | Steering meeting + summary email | Project sponsor | Decision log; baseline questions | Sponsor and functional owners confirmed
2 | Listen before launch | Structured interviews / listening sessions; capture concerns and expectations | All eight groups | Interviews; supplier call; planner listening session | Change lead + group representatives | Concern log; initial sentiment baseline | All eight groups represented
3 | Explain the change | Share what the model does and does not do; explain human review and pilot boundaries | All staff; extra focus on planners and shop floor | Town hall, Tamil handout, team huddles | Change lead + HR/operations | Questions log; quick pulse | Message comprehension baseline established
4 | Build confidence | Demonstrate forecast examples, exceptions, and how feedback changes decisions | Planners, plant heads, sales, procurement | Hands-on demo and planner forum | Planning lead + data lead | Forecast challenge log | At least 80% of invited planners attend demo
5 | Prepare workflows | Map approvals, data ownership, escalation, supplier forecast labels | IT, procurement, finance, supplier | Working session + written workflow | IT lead + procurement lead | Workflow sign-off; open issues | Critical workflow owners assigned
6 | Check readiness | Readiness review; resolve high-priority concerns; repeat planner briefing | All groups; focus on planners and plant heads | Readiness meeting; pulse survey | Project lead | Sentiment update; readiness checklist | 90% planner briefing attendance target
7 | Pilot start | Issue pilot-start message; explain where to report errors and when updates arrive | Pilot users and impacted teams | Team huddles, email, dashboard | Operations lead + planning lead | Daily issue log | All high-severity issues acknowledged within one working day
8 | Review early evidence | Share first review of forecast errors, overrides, and stakeholder sentiment | Board, planners, sales, procurement, plant heads | Pilot review and summary | Project lead + data lead | Fortnightly sentiment; root-cause log | At least two groups move from resistant to neutral or better
9 | Adapt | Publish what changed because of feedback; retrain where needed | Groups with falling sentiment or repeated issues | Targeted sessions; FAQ update | Change lead + relevant owner | Action closure evidence | 80% feedback items have owner and response within five working days
10 | Strengthen adoption | Share examples of successful use and known limitations; supplier coordination review | Planners, sales, procurement, supplier | Peer demo; supplier call | Planning lead + procurement lead | Peer feedback; supplier action log | Repeat use of agreed exception process increases
11 | Validate benefits | Compare pilot outcomes to baseline; review inventory, service, schedule stability, and usability | Board, finance, functional leads | Benefit review dashboard | Finance partner + project lead | KPI review and assumptions log | KPIs reported with baseline and data source
12 | Close and sustain | Retrospective; decide scale/adjust/hold; publish next-step owners and cadence | All groups; steering group decision | Retrospective + steering review | Project sponsor + change lead | Lessons log; final pulse survey | Decision and owners documented; all open risks assigned

## Sentiment Tracker
Check-in | Stakeholder group | Sentiment score (-2 to +2) | Previous score | Change | Evidence / source | Main concern / theme | Intervention trigger? | Action / intervention | Owner | Due date | Status | Follow-up score
Week 2 baseline | Board / Executive | [9 empty] | Not started
Week 2 baseline | Plant heads | [9 empty] | Not started
Week 2 baseline | Planners | [9 empty] | Not started
Week 2 baseline | Sales | [9 empty] | Not started
Week 2 baseline | Procurement | [9 empty] | Not started
Week 2 baseline | IT / Data team | [9 empty] | Not started
Week 2 baseline | Finance | [9 empty] | Not started
Week 2 baseline | Key yarn supplier | [9 empty] | Not started
Week 4 | Board / Executive | [9 empty] | Not started
Week 4 | Plant heads | [9 empty] | Not started
Week 4 | Planners | [9 empty] | Not started
Week 4 | Sales | [9 empty] | Not started
Week 4 | Procurement | [9 empty] | Not started
Week 4 | IT / Data team | [9 empty] | Not started
Week 4 | Finance | [9 empty] | Not started
Week 4 | Key yarn supplier | [9 empty] | Not started
Week 6 | Board / Executive | [9 empty] | Not started
Week 6 | Plant heads | [9 empty] | Not started
Week 6 | Planners | [9 empty] | Not started
Week 6 | Sales | [9 empty] | Not started
Week 6 | Procurement | [9 empty] | Not started
Week 6 | IT / Data team | [9 empty] | Not started
Week 6 | Finance | [9 empty] | Not started
Week 6 | Key yarn supplier | [9 empty] | Not started
Week 8 | Board / Executive | [9 empty] | Not started
Week 8 | Plant heads | [9 empty] | Not started
Week 8 | Planners | [9 empty] | Not started
Week 8 | Sales | [9 empty] | Not started
Week 8 | Procurement | [9 empty] | Not started
Week 8 | IT / Data team | [9 empty] | Not started
Week 8 | Finance | [9 empty] | Not started
Week 8 | Key yarn supplier | [9 empty] | Not started
Week 10 | Board / Executive | [9 empty] | Not started
Week 10 | Plant heads | [9 empty] | Not started
Week 10 | Planners | [9 empty] | Not started
Week 10 | Sales | [9 empty] | Not started
Week 10 | Procurement | [9 empty] | Not started
Week 10 | IT / Data team | [9 empty] | Not started
Week 10 | Finance | [9 empty] | Not started
Week 10 | Key yarn supplier | [9 empty] | Not started
Week 12 | Board / Executive | [9 empty] | Not started
Week 12 | Plant heads | [9 empty] | Not started
Week 12 | Planners | [9 empty] | Not started
Week 12 | Sales | [9 empty] | Not started
Week 12 | Procurement | [9 empty] | Not started
Week 12 | IT / Data team | [9 empty] | Not started
Week 12 | Finance | [9 empty] | Not started
Week 12 | Key yarn supplier | [9 empty] | Not started
Scoring guidance
-2 = strongly resistant; -1 = concerned/resistant; 0 = neutral/undecided; +1 = supportive; +2 = champion.
Trigger rule
Trigger intervention if score drops by 1+ point, or reaches -2. Assign an owner and due date; escalate -2 to project lead/sponsor.
Use evidence
Base scores on pulse survey, meeting feedback, issue themes, and observed behaviour. Do not infer sentiment from attendance alone.

## Escalation Plan
Scenario | Initial response | Investigation / action | Communication approach | Escalation path | Owner | Target response
Forecast error in first month | Acknowledge within one working day; identify affected product, dates, and operational impact. | Check data freshness, unusual orders/promotions, model behaviour, and planner overrides; apply existing human approval and contingency processes; document root cause and corrective action. | State what is known, what is not yet known, immediate operational mitigation, owner, and next update time. Avoid blaming users or claiming the model is always accurate. | Planning lead + data lead → project lead → sponsor if material service, cost, or customer impact. | Planning lead and data lead | Acknowledge within 1 working day; provide an initial update and next review time
Union / employee concern about job changes | Listen respectfully; acknowledge the concern; do not speculate or make unapproved promises. | Involve HR and appropriate employee/union representatives; clarify verified scope, role impacts, training, and decision process; record questions and agreed follow-up. | Use plain language and Tamil where appropriate; explain purpose, what is confirmed, what remains undecided, and where answers will come from. | Supervisor / HR → HR lead and employee representatives → project sponsor for policy decisions. | HR lead + change lead | Acknowledge within 1 working day; agree follow-up date
Supplier flags unrealistic yarn demand / lead time | Confirm receipt and identify affected materials and order dates. | Procurement validates stock, lead time, MOQ, and current orders; distinguish forecast estimate from confirmed order; agree feasible options. | Send a clear written summary of changed estimate, confirmed commitments, open choices, and next update time. | Buyer → procurement lead → operations lead/project lead if production continuity is at risk. | Procurement lead | Acknowledge within 1 working day; urgent continuity risk escalated same day

## KPIs and Definitions
KPI | Target | Definition / calculation | Frequency | Owner | Data source
Planner briefing attendance | ≥90% by Week 6 | Attendees ÷ invited planners × 100 | Each briefing | Planning lead | Attendance register
Stakeholder attitude movement | At least 2 groups move from resistant to neutral or better by Week 8 | Compare baseline and Week 8 sentiment; resistant means -1 or -2, neutral or better means 0 or above | Fortnightly | Change lead | Sentiment tracker + evidence
Feedback response timeliness | ≥80% within 5 working days | Feedback items with owner and response within 5 working days ÷ total feedback items × 100 | Weekly | Change lead | Feedback/action log
High-severity issue acknowledgement | 100% within 1 working day | High-severity issues acknowledged within target ÷ total high-severity issues × 100 | Weekly during pilot | Project lead | Issue log
Stakeholder coverage | 8 of 8 groups scored every fortnight | Groups with a documented score and evidence ÷ 8 × 100 | Fortnightly | Change lead | Sentiment tracker
Action closure | ≥80% closed by agreed due date | Actions closed on or before due date ÷ actions due in period × 100 | Fortnightly | Project lead | Action log